## Milestones
Milestone | ID | Area | Content | Status | When | Notes
M0 |  | CP conversion | The assembler: ESA/390 instructions for CE's ASSEMBLE | Done | Sep | Closed, no listing check outstanding
M1 |  | CP conversion | CP IPLs in ESA/390 mode (DAT off), console, channel subsystem, DASD, dump | Done | 30 Sep–Oct
M2 |  | CP conversion | DAT on: ESA/390 segment/page tables, CP in AMODE 31, 31-bit guests | Done | Oct | AMODE 31 made consistent by I-259/I-260 on 11 Oct
M3 |  | CP conversion | One S/370-mode guest logs on and runs CMS | Done | 3–4 Oct
M3 | 3a | CP conversion | DASD IPL of CP (DMKSAV, DMKCKP, DMKCPI) | Done | 3 Oct | R-09 retired
M3 | 3b | CP conversion | CMS by IPL 190 | Done | 4 Oct | R-08 retired
M3 | 3c | CP conversion | Named systems shared by page frame | Done | 4 Oct | Increment 2 open (33-FRAME-SHARING)
M4 |  | CP conversion | Two guests isolated; 4 KB storage keys (ISKE/SSKE, DISPLAY K) | Done | Oct | Largely done; R-12 measured
M4 | 4b.1 | Real storage | Probe in AMODE 31; CORTABLE built at IPL from the real size | Done | 7 Oct
M4 | 4b.2 | Real storage | Storage above 16 MB as CP's paging store (MVCL slots) | Done | 7 Oct | XA0053DK, docs/38
M4 | 4b.4 | Real storage | Up to 2 GB; CP's machine ends at 16 MB, the rest is paging store | Done | 7 Oct | MAINSIZE 2048 tested
M4 | 4b.3 step 1 | Real storage | CP stays AMODE 31 after TRANS / DMKPTRAN's LRA | Done | 11 Oct | f6f85d6
M4 | 4b.3 step 2 | Real storage | IDAW consumers and real-address masks 31-bit clean | Done | 11 Oct | With steps 3–4
M4 | 4b.3 step 3 | Real storage | DMKPAG paging I/O through a two-IDAW list for high frames | Done | 11 Oct | ba6c595
M4 | 4b.3 step 4 | Real storage | DMKCCW / DMKDGD: one-page data areas in high frames through IDALs | Done | 11 Oct | ac962df; I-262 fixed later
M4 | 4b.3 step 5 | Real storage | CORTABLE to frames top, high free list, switch (frames 16–160 MB) | Done | 11 Oct | 9ed9957; I-259..I-262; regression clean at 16/256 MB
M4 | 4b.3 step 6 | Real storage | Two Debians at once (I-254) | Done | 11 Oct | dd6: both at login, both answer SSH; I-263, I-264
M4 | 4c | Real storage | CPWATCH running again (I-251) | Planned |  | After CP leftovers
M5 | 5a | CMS | Build CMS from source with our pipeline | Done | 5 Oct
M5 | 5b | CMS | EC-mode CMS (IPL 290) | Done | 6 Oct | XA0051DK
M5 | 5c | CMS | CMS storage above the line (HIGHSTOR, CMSSTOR) | Done | 6 Oct
M5 | 5d | CMS | AMODE 31 service calls from programs | Done | 6 Oct | I-248, I-249
M5 | 5e | CMS | cREXX compiles on the machine | Done | 7 Oct
M5 | 5f | CMS | 31-bit C toolchain, cross (GCC 13 -m31, newlib, cmsrt) | Done | 7 Oct
M5 | 5g | CMS | Native 31-bit C (GCCLIB31), cREXX built on the machine | Done | 7 Oct
M6 |  | CMS | 31-bit CMS proper; larger minidisks (4K blocks) | Done | 11 Oct | EDF under IPL 290 (docs/63); 31-bit nucleus sweep stays background (doc 62 B)
M6 | 6a | CMS | FORMAT (BLKSIZE 4096 writes an EDF label, directory and allocation map | Done | 11 Oct | 25de15c; T3350 temp disk and dedicated 3380
M6 | 6b | CMS | EDF disks read: ACCESS, LISTFILE, STATE, TYPE, COPYFILE from (DMSEFS, XA0056DK) | Done | 11 Oct | 86699c4; 100,000-record V and 70,000-record F files read
M6 | 6c | CMS | EDF write, erase, rename; files above 65,535 records | Done | 11 Oct | 14bae66; 70,000-record copy byte-identical (edf.py)
M6 | 6d | CMS | Large minidisks: a full-volume 3380 as one EDF disk | Done | 11 Oct | a101a8f; full 885-cyl 3380 (518 MB); one 112 MB file, 1.4M records, verified
M6 | 6e | CMS | Tools across both formats (DISK DUMP/LOAD, TAPE, MOVEFILE, FULIST) | Done | 11 Oct | DISK DUMP, MOVEFILE (100,000-record V file), COMPARE, COPYFILE on EDF; DISK LOAD writes to A by design; TAPE not run (same RDBUF/WRBUF path)
M7 | 7.0 | ESA/390 guests | Baseline test guest (STSCH/SSCH/ESA PSW/X'B8') | Done | 7 Oct
M7 | 7.1 | ESA/390 guests | SET ESA / machine mode, ESA IPL | Done | 7 Oct
M7 | 7.2 | ESA/390 guests | Virtual channel subsystem (DMKVCS) | Done | 7 Oct
M7 | 7.3 | ESA/390 guests | ESA/390 guest DAT (DMKVAX shadow tables) | Done | 7 Oct
M7 | 7.4 | ESA/390 guests | What Linux uses besides (secondary space, STAP, SIGP, timers, DIAG 10) | Done | 7–8 Oct
M7 | 7.5 | ESA/390 guests | Linux/390 31-bit from the reader, shell on the 3215 | Done | 8 Oct
M7 | 7.6 | ESA/390 guests | BusyBox userland, CTC network | Done | 8 Oct
M7 | 7.7 | ESA/390 guests | Debian 7.11 from a 3390, SSH over CTC | Done | 8–9 Oct
M7 | 7.8 | ESA/390 guests | Linux for several users (LINUX EXEC); Linux and CMS side by side | Done | 9 Oct | Two Debians at once: done 11 Oct (M4b.3 step 6)
M7 | 7.9 | ESA/390 guests | Channel programs of any length for ESA/390 guests | Done | 10 Oct
M7 | 7.10 | ESA/390 guests | IPL LINUX from its disk (vmzipl) | Done | 10 Oct
M7 | 7.11 | ESA/390 guests | 3390-9 Debian disk (7 GB) as standard | Done | 10 Oct
M8 | 8.1 | cREXX | Current cREXX cross-built for CMS (RXC8, RXAS8, RXBVM8) | Done | 8 Oct
M8 | 8.2 | cREXX | Current cREXX built natively on CMS | Done | 9 Oct– | 15 Oct, route 2 (GCC 13 on CMS, 9.21): all 113 units compiled by cc1 on CMS (CRX82 EXEC, m8/native/mknat.sh), linked by ld there: RXC82, RXAS82, RXBVM82 MODULE. Run n83g: C82HELLO compiled/assembled/run (sum 1..10 = 55), C82LIB with library functions (length/reverse via LIBRARY RXBIN). Fixes on the way: cmsrt file buffers sized from the FST, heap = largest HIGHSTOR piece, XL loads the image before the file buffer, VFS literal ../ paths, cc1 GC params, handler panel 1, scanners from upstream's S370 encoding (rexbscan 3.2 MB -> 169 KB). Open: CMS ar cannot write an archive (temp file), RXC link takes the members the PC map names
M9 | 9.1 | Since kit b6 | SET/QUERY MACHINE, FULIST, GLOBALV, command tables, I-257, I-258 | Done | 10–11 Oct
M9 | 9.2 | CP leftovers | I-235 (models), I-201 (DMKDMP dump), warm start (I-267, I-268), LPSW fast path above 16 MB, per-user IP (9.12a) | Done | 11 Oct | I-201, I-265, I-267, I-268, I-269 fixed; LPSW/SVC fast paths; I-235 models kept resident by design (M10 revisits sharer invalidation)
M9 | 9.3 | C++ | C++ on CMS (subset, cross route) | Done |  | Superseded by 9.21: full GCC 13 C++ natively on CMS, not a subset
M9 | 9.4 | Database | SQL: SQLite on CMS + SQLSERV; MariaDB/PostgreSQL on Debian | Done |  | SQLite 3.46.1 on CMS (SQLITE EXEC) and the SQLSERV service machine (tc47, 12 Oct). 14 Oct: PostgreSQL 16.15 cross-built for the 31-bit Debian guest (linux390/pgsql/mkpg.sh), started at boot; PGSQL EXEC on CMS over the spool bridge (each CMS user its own role and database): CREATE/INSERT/SELECT verified (pg1); PGSQL on LANG; the Debian disk moved to the 3390-9 (5.8 GB free, bt1: PostgreSQL runs). Kit b14. MariaDB not planned (C++, too big for 64 MB).
M9 | 9.5 | Network | CMS sockets + httpd | Done |  | 13 Oct: CMS sockets (NICOF) under IPL CMS and IPL 290 (I-285), HTTPD/HTTPD31, and NICOF's whole client suite built with GCC 13 on the language disk (CMSFTP31, NHFS31, HACC31, IPLOOK31, NCTEST, samples); HX under 290 fixed (I-286). Kit 13 (kt27).
M9 | 9.6 | dbase | xBase / Harbour | Done |  | mikebeer/xbase on CMS and Debian: cREXX version (XBASE RXBIN, tc37 7/7) and the C89 version (XBASEC XIMAGE via XL; tc42 7/7 = PC; 32-bit long fixes pushed upstream 7d2a188); Debian xbase-c. Harbour itself not ported. languages/xbase (mkxbasec.sh)
M9 | 9.7 | MQ | MQ and MQTT (CMS and Debian) | Done |  | MQTT on CMS (MQTT EXEC over the spool bridge, pd15) and mosquitto on Debian; 14 Oct: MQ-style queues on RabbitMQ for CMS (MQ EXEC + MQAMQP: rabbitmq-c 0.11 with GCC 13 on NICOF sockets; PUT/GET/DEPTH/PURGE, GET onto the stack; verified against RabbitMQ 3.12 on the PC, runs mq1/mq2).
M9 | 9.8 | APL | APL in C on CMS | Done | 11 Oct | Debian 34/34; CMS 33/33 (primes.apl has lines over 80 columns); e551b9e; needs Hercules 4
M9 | 9.9 | REXX | ooRexx 5 on Debian | Done (dev; kit next) |  | 15 Oct: ooRexx 5.3.0 (github ooRexx/ooRexx) cross-built for 31-bit s390 Linux with s390x g++ -m31 against the lx31 glibc 2.39 sysroot, libstdc++/libgcc static, own /opt/oorexx/lib/ld.so.1 + libc (Debian 7's glibc 2.13 is too old); ncurses extension skipped. Installed in the Debian guest over ssh (run rx1), rexx.img made there by rexximage (50 s); rexx -v: 5.3.0, 32-bit; arrays, directories, DateTime, 2**64, NUMERIC DIGITS 30 tested. oorexx/oorexxc in /usr/local/bin (rexx stays Regina)
M9 | 9.10 | AI | AI gateway service machine (ASKSERV): CMS/Linux/TELL clients; the model runs in llama.cpp on the PC (or a cloud API), reached through BORDER | Planned
M9 | 9.11 | Snapshot | Kit build 7 (distributable snapshot) | Done | 11 Oct | b7, 13 parts; verified on a fresh CE (kt16): EDF, TDISK, IPL LINUX
M9 | 9.12 | Firewall | Network pack: per-user addresses, CP guest LAN, BORDER firewall, inside DHCP/DNS (9.12a-d) | Done (kit b19) |  | Network pack 9.12a-d done: per-user addresses, CP guest LAN, BORDER (NAT, firewall, port forwards), DHCP/DNS.
M9 | 9.12a | Addresses | Per-user IP address at disk IPL from the directory (fixes I-266) | Done | 11 Oct | Address follows the CTC pair (62x/63x or real); vm370plus-net on both Debian disks; verified 10.1.2.2 by itself
M9 | 9.12b | Guest LAN | CP virtual NIC per guest on one internal segment (LCS/QETH style, like z/VM Guest LAN) | Done (kit b17) |  | CP guest LAN: CP DEFINE LCS (3088-60 simulated by CP, module DMKVLN), one segment 10.3.0.0/24, Debian eth0 by vm370plus-lan. Steps A-D tested (lb3-lb11): ping, 1400-byte frames, TCP 200 KB intact (~37 KB/s), logoff/DETACH/offline under traffic. I-292 fixed, I-293 worked around. Kit b17 verified on a fresh CE (kt31).
M9 | 9.12c | Firewall | BORDER service machine: only outside link; NAT outbound; port forwards to service machines (httpd 9.5). One network configuration file on MAINT: OUTSIDE DHCP (bridged LCS/tap, address from the LAN) or OUTSIDE STATIC ip/mask gw; inside subnet and addressing; EXPOSE proto port TO user¦ip port (default: nothing exposed) | Done (kit b18) |  | BORDER service machine (AUTOLOG BORDER BORDER): in-storage Linux, kernel #12 (netfilter, iptables 1.4.14), ctc0 10.1.4.2 (pair 0606/0607), eth0 10.3.0.1; NAT, firewall, port forwards from BORDER CONFIG (MAINT 19E). Verified on a fresh CE (kt32): LAN guest -> PC through NAT, PC -> 10.1.4.2:2223 -> guest ssh.
M9 | 9.12d | DHCP/DNS | DHCP and DNS for the inside segment as a service machine (dnsmasq on Debian, or in BORDER) | Done (kit b19) |  | BORDER: udhcpd (10.3.0.100-199, router/DNS 10.3.0.1), DNS forwarding to BORDER CONFIG's DNS (default the PC 10.1.4.1); udhcpc in the in-storage Linux, dhclient in Debian. Verified on a fresh CE (kt33).
M9 | 9.13 | Tools | Public VM/370 tools for the kit (survey 11 Oct) | Planned |  | Before kit 7 (9.11)
M9 | 9.13a | Pascal | New Stanford Pascal (Oppolzer, github StanfordPascal/Pascal) replaces CE 2021.03 | Done |  | New Stanford Pascal 2026.10 on CMS via PCINT (cross-built, 31-bit; big-endian fix pcint-bigendian.patch): PCPAS/PCRUN EXECs, tc33 output = PC. Native 370 code needs a PASCAL2 newer than the published 2024.02. CE 2021.03 unchanged. languages/pascal
M9 | 9.13b | NJE | RSCS NJE updates (Coghlan) + TCPNJE: VM/370 NJE to MVS/z/OS/Linux | Planned |  | TCPNJE is in SDL Hyperion; we run Hercules 3.13
M9 | 9.13c | NJE Linux | UnixNJE (FUNET-NJE) in the Debian guest: CMS <-> Linux NJE | Planned |  | Needs 9.13b
M9 | 9.13d | Sockets | NICOF + CMSFTPD (devhawala, public domain): sockets API and FTP for CMS | Done |  | 13 Oct (ncf3): NICOF 0.7.0 installed -- NICOFSRC/NICOFPXY/TCPIPPXY (VM50U1 61-70, ECMODE), NCFACC on 19E, AUTOLOG1 starts the proxies, 3270 groups 03CD/03CE, PC side vm370plus/nicof (nicof.jar, nicof.sh). NHFS LIST/GET/PUT, CMSFTPD with Python ftplib: LIST, 837 files, text STOR/RETR, 67 KB binary with FF EF round trip identical (~12 KB/s). Found I-283 (STNSM in BC mode, fixed in CP).
M9 | 9.13e | Games | Game disk: VM/370 games tape (IBM VS BASIC runtime removed), WIOS SNAKE/SLASH, CALL-OS BASIC TREK2, Zork/Dungeon | Planned
M9 | 9.13f | Workshop | VM Workshop 1985/86 tools that run on R6: CARD, FCOPY, CLUST/TERM macros; check DISKPRY, LEDIT, IEBCOPY, JSCAN | Planned |  | CPWATCH (85 M0083) is 4c
M9 | 9.14 | TELL | TELL everywhere: CMS TELL EXEC (CP MSG local, RSCS/NJE remote), Linux tell (vmcp, kernel CONFIG_VMCP) with incoming MSG captured, PC client through BORDER (CHATBOT-style gateway) | Done |  | 13 Oct: TELL EXEC (CP MSG local; TELL user AT LINUX via the spool bridge, message as input cards; prompt mode for long text, I-277); Linux tell + setuid vmmsg (CP MSG with the Linux user's name); messages kept in /var/spool/vmspool/msg. On 19D and LANG. RSCS remote and the PC client (BORDER) follow with 9.13b/9.12c.
M9 | 9.15 | Python | Python on CMS: the C89 implementation from mikebeer/python (in creation), built with GCC for CMS; Debian uses standard wheezy python 2.7/3.2 packages | Done |  | mikebeer/python (C89, NumPy/pandas/SciPy built in) as PY XIMAGE, PYTHON EXEC; 27 of 29 tests = CPython on CMS (tc23/24; 15_import needs package files, 24_sockets: no sockets yet). 32-bit long fix pushed to mikebeer/python (6e4a7a5). languages/python
M9 | 9.16 | TDISK | TDISK EXEC: TDISK [cyls] [fm] defines, formats and (with fm) accesses a temporary disk; HELP TDISK | Done | 11 Oct | Owner request 11 Oct
M9 | 9.17 | Tiny LLM | llama2.c-style inference of a tiny model (stories15M) natively on Debian/390 and on CMS (C, high storage, HFP/BFP and byte order converted): a demonstration; real models via 9.10 | Planned |  | Owner request 11 Oct; llama.cpp itself needs 64-bit, C++17 and GBs
M9 | 9.18 | Mail | SENDMAIL / GETMAIL for CMS via a MAILER service machine (SMTP out through BORDER; POP/IMAP or SMTP in, delivered to the reader in class M) | Planned |  | Owner request 11 Oct; after 9.12
M9 | 9.19 | COBOL | GnuCOBOL 3.1.2. Debian: cross-built cobc + static libcob + GMP 6.3 against wheezy glibc, gcc 4.6 compiles the generated C (done 11 Oct). CMS goal: compile natively -- first cobc/libcob through the cross route (GCC -m31, newlib, cmsrt), then built on CMS by GCC380/GCCLIB31 with a COBOL EXEC (cobc -C, GCC, LOAD, GENMOD) | Done | 11 Oct– | GnuCOBOL: Debian (cb1) and CMS natively (COBOL EXEC, tc17). Plus mikebeer/cobol (COBOL-85 + OO, indexed files): CMS COBX EXEC 19/19 = PC (tc41-44; record files binary via cobrt-cms.patch); Debian 20/20 (pd2/pd3, languages/common/mkdebtests.sh). languages/cobol, languages/cobol2c
M9 | 9.20 | PL/I | PL/I beyond CE's PL/I(F): research first -- no maintained open PL/I for s390 (Iron Spring is x86 and closed, pl1gcc unfinished); options: document PL/I(F), a PL/I subset to C translator, old subsets (PL/I-G) | Done | 11 Oct– | mikebeer/pli 79eae4d (Enterprise PL/I subset to C89): CMS PLIC EXEC through GCC 13, 34/35 = PC (tc43-45); Debian 38/39 incl. multi-file and separately compiled modules (pd2/pd3). Only difference both places: t32 AREA count depends on pointer size. CE PL/I(F) also works. docs/64-PLI.md, languages/pli
M9 | 9.21 | C/C++ | Modern C/C++ toolchain on CMS: GCC 13.3 cc1/cc1plus and binutils 2.42 (as, ld, ar) cross-built for the M5f runtime; XL loader for programs above 16 MB; sysroot tar as read-only VFS; CC EXEC; then COBOL (9.19) compiles natively | Done | 12 Oct– | Owner decision 12 Oct (GCC380 cannot add long longs). GCC 13.3 cc1/cc1plus (XL loader, above 16 MB), binutils 2.42 as/ld/ar, elf2cms, CC EXEC; SYSROOT TAR + CXXROOT TAR; libstdc++ 13.3 built for newlib/soft float. Native C (tc15/16), C++ incl. iostreams (tc20/21). No C++ exceptions yet. toolchain/
M9 | 9.22 | UNTERSE | TERSE/UNTERSE for CMS and Debian: a C89 TERSE (PACK/SPACK) decompressor after IBM's open-source one, then compression; built with GCC 13 for CMS | Done |  | UNTERSE: C89 port of the Open Mainframe Project's tersedecompress (Apache 2), PACK/SPACK, F/V, text/binary; testdata 120/120; CMS byte-identical to z/OS originals (tc72). TERSE: new SPACK encoder running the decoder's model (longest known phrase), sizes = IBM SPACK within block padding; PC round trip 26 text + 3 binary, CMS round trip (tc74). TRS/UNTRS MODULE + TERSE/UNTERSE EXEC on the LANG disk; Debian terse/unterse. Open: confirm AMATERSE on z/OS reads our SPACK
M9 | 9.23 | ZIP | Info-ZIP zip/unzip and gzip built natively for CMS (GCC 13, cmsrt), beside CE's MINIZIP/MINIUNZ and VMARC | Done |  | Info-ZIP zip 3.0 / unzip 6.0 and gzip (zlib 1.3.1 minigzip) for CMS: IZZIP/IZUNZIP/MINIGZ MODULE + ZIP/UNZIP/GZIP EXEC on the LANG disk; round trip on CMS, PC-made .zip unzips (tc64-71); CMS file dates in the archive (cmsrt stat reads the FST via STATE). gzip names fn ft-GZ. No encryption. languages/zip
M9 | 9.24 | Snapshot | Kit b8: LANG disk (MAINT 19F, VMLANG) with all CMS languages, LANG EXEC, Guide chapter 8, Debian language bundle installed | Done | 12 Oct– | b8, 15 parts (14-15: LANG disk with JOINLANG); verified on a fresh CE (kt17-21): VMLANG attached by AUTOLOG1, LANG -> L (19F), SQLite 3.46.1, CC HI -> Hi!, Debian login. CMSUSER A cleaned of old language EXECs/MODULEs
M9 | 9.25 | Spool bridge | Linux services on the service-machine interface: vmspool daemon in the Debian guest (vmur reader/punch) turning requests into Asterisk AMI (PHONE EXEC), MQTT, MariaDB calls; replies punched back like SQLSERV | Done |  | vmspoold (C) in the Debian guest + LXCALL/PHONE/MQTT EXECs on CMS; services echo, sys, phone (Asterisk), mqtt; verified pd15; needed CP fix I-276
M9 | 9.26 | RXPIP | mikebeer/rexxpository (RXPIP, pip-style REXX packages) on VM/370plus: 1) rxpip (Regina) in the Debian guest; 2) TAR for CMS; 3) RXPIPSRV service machine + RXPIP EXEC over reader/punch via the 9.25 bridge; 4) CMS install as EXEC files (external functions), CMSNAME map; platform tags brexx-cms-s390, crexx-cms-s390, regina-linux-s390 | Done |  | rxpip server+client in Debian (Regina, rxpipd.py, minicurl), vmspoold service rxpip; CMS RXPIP AVAIL/SEARCH/SHOW/BUILD/RUN/GET verified pd19 (RXPIP RUN DEMO works); TAR for CMS not needed (Linux unpacks); open: PUBLISH from CMS
M9 | 9.27 | LaTeX | TeX/LaTeX in the Debian guest (texlive-base, dvips, pdflatex); LATEX EXEC on CMS over the 9.25 bridge: fn TEX in, fn PDF/PS/DVI back as files | Done |  | TeX Live 2023 pdfTeX (latex/pdflatex), dvips, makeindex cross-built (wc++ for wheezy C++), 24 MB texmf, formats made on the PC; LATEX EXEC: fn PS back to CMS or PDF; verified pd19 (LATEX HELLO -> PSPRINT -> PDF)
M9 | 9.28 | troff | groff/troff (man, ms, mm) in the Debian guest; TROFF EXEC on CMS over the bridge; text output to the CMS console or printer, PS/PDF as files | Done |  | groff (groff-base 1.21 + groff 1.23 ms/me/mm/mom macros) in Debian; TROFF EXEC on CMS: text as fn DOCUMENT, PostScript as fn PS (pd19)
M9 | 9.34 | NetRexx (Linux) | NetRexx in the Debian guest: a Java VM first -- JamVM with the GNU Classpath library (C parts cross-built with wcc, the Java parts built on the PC), NetRexx (RexxLA/netrexx) built on the PC for that VM; nrc/nr: interpret (-exec) and compile | Done (kit b16) |  | Java (JamVM 2.0 + GNU Classpath 0.99), javac (Eclipse ecj 3.5.2), NetRexx 3.05 (nrc compiles with ecj, nr interprets) installed in the Debian guest. Verified 14 Oct on the dev disk at 192 MB: javac+java 287 s, nrc+java 685 s. MAINT may now define 256 MB.
M9 | 9.35 | NetRexx (CMS) | NetRexx on CMS: the same JamVM + GNU Classpath built with GCC 13 for the EC-mode CMS (IPL 290, above 16 MB, single-threaded), the class library read from the LANG disk; NETREXX EXEC (interpret, then compile) | Done (kit b16) |  | Java and NetRexx on CMS: JAVA, JAVAC (ecj 3.5.2), NETREXX [COMPILE] EXECs; JAMVM XIMAGE (XL). Verified on the fixed CP: JAVAC 27 s CPU, NETREXX interpreted 27 s, COMPILE 45 s, compiled run 3.7 s. Fixed on the way: I-289, I-290 (CP), mmap page rounding, XL heap trim.
M9 | 9.36 | Project mgmt (MCproject) | Our own project management system, MCproject (mikebeer/MCproject, under way), on VM/370plus: the server in the Debian guest, reached from the LAN and, through BORDER, from the PC (vmfwd); a CMS front end where it fits (spool bridge or native) | Planned | 15 Oct– | Owner decision 15 Oct: our own system instead of OpenProject (current OpenProject needs Ruby 4.0, Node 24, PostgreSQL 16+, 1 GB RAM, 64-bit: out of reach of the 31-bit Debian 7 guest). The repository is still empty (15 Oct); the VM/370plus port follows its design: language and database to be matched to what runs here (C/C++ GCC 13, Python 2.7/3.2, Regina, PostgreSQL 9.1 or SQLite 3.46 on both sides)
M9 | 9.37 | REXX (Regina) | Regina REXX on both sides: (a) Linux: Regina 3.6 in the Debian guest (wheezy package, `regina`/`rexx`); (b) CMS: Regina built natively with GCC 13 and the M5f runtime (cmsrt), REGINA MODULE/XIMAGE on the LANG disk, a REGINA EXEC front end (`REGINA fn [ft]` runs a REXX program from a CMS file), ADDRESS CMS/COMMAND passing commands to CMS (SVC 202), stream I/O on CMS files | Done (dev; kit next) | 15 Oct– | 15 Oct. (a) Linux: Regina 3.6 in Debian since 10 Oct. (b) CMS: Regina 3.9.5 cross-built (languages/regina/mkregina.sh: generic OS layer patched for CMS, no external queues, 32-bit), REGINA MODULE on LANG (TEXT + LANGGEN). Run rx3: PARSE VERSION/SOURCE (CMS COMMAND), arithmetic, NUMERIC DIGITS 40, ADDRESS COMMAND STATE/LISTFILE/QUERY DISK rc 0, CP QUERY USERID, LINEOUT/LINEIN on a CMS file. cmsrt got system() (SVC 202, tokenised plist). Limits: commands that are user-area MODULEs would overlay REGINA; 8-character tokens (CMS plist); the X'01' command flag made CMS's CP routine fail (spec. exception), so plain SVC 202
M9 | 9.38 | Helpdesk (MChelpdesk) | Our own helpdesk / trouble-ticket system, MChelpdesk (mikebeer/MChelpdesk), on VM/370plus: the server in the Debian guest beside MCproject (9.36), reached from the LAN and, through BORDER, from the PC; tickets from CMS users (a TICKET EXEC over the spool bridge or MSG/reader), mail notification once 9.18 exists | Planned | 15 Oct– | Owner request 15 Oct. Follows the MChelpdesk design; shares platform choices with 9.36 (language/database matched to what runs on VM/370plus)
M9 | 9.29 | Ghostscript, ps2pdf | Ghostscript in the Debian guest: PS->PDF (ps2pdf), PDF->PS (pdf2ps), PS/PDF->PCL/raster for printers; PS2PDF EXEC on CMS | Done |  | Ghostscript 10.02.1 cross-built (languages/ghostscript/mkgs.sh), gs + ps2pdf/pdf2ps/ps2ps in /usr/local/bin of the Debian guest; PS->PDF verified pd19
M9 | 9.30 | BookMaster | A BookMaster-compatible formatter (BookMaster is IBM-licensed; we build our own): :userdoc./:h1./:p./:ol./:dl. GML tags to SCRIPT-style line output, PS and PDF (via 9.29); BOOKIE EXEC on CMS | Done |  | bookie: our BookMaster-compatible formatter (languages/bookie/bookie.py -> troff ms+tbl -> groff), BOOKIE EXEC on CMS: text and PostScript, PSPRINT to printer/PDF (pd19). Not done: index, running heads, revision codes
M9 | 9.31 | Graphical printing | PS/PDF from CMS or Linux to a real printer: (a) bridge: PSPRINT EXEC -> Debian -> Ghostscript -> CUPS/LPD/IPP/port 9100 printer on the PC LAN (needs routing/NAT on the PC for the guest's CTC network); (b) spool: PostScript text on a virtual printer, Hercules 1403 to a file or socket on the PC, a PC script hands it to the printer (PS only, lines up to 132; PDF goes through (a) or ps first) | Done |  | both paths verified pd19: spool (PSPRINT -> 00E -> PC psprint.py, PS byte-identical, ps2pdf) and bridge (PSPRINT (BRIDGE -> Debian gs -> pdf/ps/pcl -> printer port 9100 or lp queue, print.conf); a real printer on the user's LAN still to try
M9 | 9.32 | TELL internet | TELL to and from users on the internet: CMS TELL user AT NET publishes to MQTT topic vm/tell/out/<user>; outside users (any MQTT client, password, ACL) publish to vm/tell/from/<user>/to/<vmuser>, a gateway in the Debian guest turns it into CP MSG '(net:user) text'; a forwarder on the PC exposes the broker (router port forward is the owner's) | Done | 13 Oct | 13 Oct (pd24): TELL user AT NET -> MQTT vm/tell/out/user; outside users publish vm/tell/from/<login>/to/<userid>, tellgw sends CP MSG '(net:login)'; logins (tellnet-user) + ACL on the guest's outside listener, local listener unchanged; tools/netfwd.py (--tls, port 8883) on the PC, tools/nettell.py client. Verified both ways, not-logged-on answer, wrong password and forged sender rejected, TLS. The router's port forward is the owner's. Interim until BORDER (9.12c).
M9 | 9.33 | CP/M | CP/M 2.2 on VM/370plus through a Z80 emulator: (a) RunCPM (MIT) in the Debian guest, interactive and as a spool-bridge service (CPM EXEC); (b) natively on CMS (GCC 13 / cmsrt): CP/M disk as CMS files, console on the CMS terminal. CP/M 2.2 binaries freely redistributable (Caldera/Lineo 2001) | Done | 13 Oct | 13 Oct: (a) Debian: RunCPM 6.9 (31-bit), runcpm for Linux users, vmspoold service cpm, CPM ... (LINUX on CMS: PUT/GET/RUN verified (ASM/LOAD/HELLO). (b) CMS natively: RUNCPM MODULE on LANG (abstraction_cms.h: drive X: = CMS disk X, binary files, pending empty files, line console), CP/M 2.2 programs on L:, CPM IMPORT/EXPORT text conversion; CPM L:ASM HELLO; L:LOAD HELLO; HELLO prints its line (cpmlang). Patch languages/cpm/runcpm-vm370plus.patch, mkcpm.sh.
M10 |  | 64-bit | z/Architecture (64-bit) | Planned
M10 | 10.1 | Documentation | Migration documentation 31 -> 64 bit
M10 | 10.2 | Documentation | Manual Update
M10 | 10.3 | Snapshot | Kit after 64-bit (z/Architecture)
M11 | 11.1 | Multiprocessor-Support | MP (CP on several CPUs, virtual MP)
M11 | 11.2 | More Languages | GNU APL, full C++, Java on CMS, NetRexx 4
M11 | 11.3 | VoIP | FreeSWITCH
M11 | 11.4 | IoT | Node-RED
M11 | 11.5 | Container | Docker, QEMU/ReactOS, Bochs/DOS
M11 | 11.6 | CF | CFSERV
M11 | 11.7 | Documentation | Manual Update
M11 | 11.8 | Snapshot | Kit after M11
M12 | 12a | DOS/VSE | DOS/VS Release 34 installed in a virtual machine (system packs, directory entry, IPL) | Planned |  | Owner request 11 Oct; S/370-mode guest
M12 | 12b | DOS/VSE | DOS/VS under our CP as a regression of the S/370 guest paths (SIO/TIO, CCW translation, V=V) | Planned
M12 | 12c | DOS/VSE | POWER spooling through VM reader/punch; jobs submitted from CMS | Planned
M12 | 12d | DOS/VSE | CMS/DOS simulation cross-checked against real DOS/VS | Planned
M12 | 12e | DOS/VSE | Research: inventory DOS/360 R26 and DOS/VS R34 tapes for source; feasibility of a 31/64-bit DOS | Planned |  | srorso/dos360install
M13 | 13a | MVS guest | TK5 (MVS 3.8j) as a S/370 guest under VM/370plus: DASD, consoles, JES2 through the VM spool; a regression of the S/370 guest paths like M12 | Planned |  | Owner question 13 Oct; near-term, like DOS/VS (M12)
M13 | 13b | MVS 31-bit | Research: feasibility of a 31-bit MVS from the public-domain MVS 3.8j source (the MVS/XA step: 31-bit addressing, channel subsystem I/O, storage management, SVCs, access methods) -- scope estimate before any work | Planned |  | Owner question 13 Oct; very late in the list (after M10-M12)